# Project Plan

Modular Power Electronics & Current Control for the Geec

| Student | Conor Farrell |
| --- | --- |
| Supervisor | Dr Maeve Duffy |
| Co-Assessor |  |
| Revision | 1 |

# Scope Statement

The scope of this project will include:

- Evaluation of Current Power Electronics on the Geec

- Evaluation of Brushless versus Brushed Motor

- Simulation & Design of Power Electronics Board

- Design of Power Control Board

- Verification of safe functionality & implementation on the Geec

# Stakeholders

| Stakeholder | Power | Interest | Concerns |
| --- | --- | --- | --- |
| Supervisor (Owner) | High | High | On time & achieve milestones/outputs Timely Solutions to project issues Regular Reports, safe and reliable implementation of deliverables |
| Co-Assessor | Medium | Low | Achieve Deliverables |
| Geec Team | Medium | High |  |
| SEM Organiser | High | High | Design is compliant with the rules as written by SEMD |

Contents

1	Scope Statement	1

2	Stakeholders	1

3	Deliverables	3

3.1	Fixed Deliverables	3

3.2	Interim Deliverables	3

4	Work Breakdown Structure	3

4.1	WP1: Background Research and Evaluation of Existing System	3

4.1.1	Task 1: BLDC Evaluation	3

4.1.2	Investigate the Current Power Electronics Design	3

4.1.3	Research different methods of control, power etc.	3

4.2	WP2: Power Electronics Design	3

4.2.1	Task 1: Power Stage Circuit Simulation	3

4.2.2	Task 2: Power Electronics Part Selection	3

4.2.3	Task 3: Schematic Design	4

4.2.4	Task 4: Layout Design	4

4.3	WP3: Control Electronics Design	4

4.3.1	Task 1: Control Scheme Comparison	4

4.3.2	Task 2: Hardware Control Simulation	4

4.3.3	Task 3: Control Electronics Schematic	4

4.3.4	Task 4: Control Electronics Layout	4

4.4	WP4: Electrical Verification	4

Deliverable: Verify the functionality of both the power electronics board and the power controller board.	4

4.4.1	Open Loop Power Electronic Testing	4

4.4.2	Power Controller Testing	4

4.4.3	Closed Loop Motor Control	5

4.4.4	Verification on Mini Dynamometer	5

4.5	WP5: Implementation on the Geec	5

4.5.1	Convert current power electronics system to new system	5

4.5.2	Measure performance improvements	5

5	Work Schedule	6

6	Risk Register	7

7	Communication Strategy	8

# Deliverables

## Fixed Deliverables

- Project Plan

- Progress Report & Presentation

- Project Dissemination ( Word Document + PPT document)

- Bench Demonstration

- Final Project Report

## Interim Deliverables

- Hardware Simulation

- Control Simulation

- Power Electronics Schematic and Layout

- Power Controller Schematic and Layout

# Work Breakdown Structure

## WP1: Background Research and Evaluation of Existing System

Deliverable: This Work Package should allow for an informed decision on the benefits and drawbacks of the current power electronics and the required direction forward for the Geec.

### Task 1: BLDC Evaluation

- Rory Egan’s thesis last year investigated the use of a BLDC motor, suggesting that there is much greater performance to be achieved using BLDC.

- Investigate high efficiency BLDC motors in the 100-1000W range.

- Compare using existing data and manufacturer specifications the energy requirements.

### Investigate the Current Power Electronics Design

- Evaluate the parts and layout of the current power electronics.

- Identify the capabilities and limitations involved in the current design.

- Simulate the current design.

### Research different methods of control, power etc.

- Investigate the newer power MOSFETs, Gate Drivers, HEMTs and sensors.

- Investigate different control strategies, open loop, hardware vs software closed loop.

- Investigate connectors separate solutions.

## WP2: Power Electronics Design

Deliverable: Power Electronics board with gate driver, Power MOSFETs, Current Sensors, Bulk Capacitors and non-isolated

### Task 1: Power Stage Circuit Simulation

- Create an accurate  simulation of the new power electronics.

- Determine the power consumption  during switching events.

- Evaluate current ripple due to different switching frequencies

### Task 2: Power Electronics Part Selection

- Select and Simulate other electrical parts. Current sensors, voltage sensors, combinations of capacitors (electrolytic, ceramic, Film, MLCC).

- Create a block diagram and of parts on each board.

- Estimate Power Consumption for idle and active states.

### Task 3: Schematic Design

- Create part library in Altium with easy-to-understand symbols

- Create a 1- or 2-page schematic showcasing all components keeping all components that are functionally close to each other.

- Use SMD devices 0805 or greater in size.

### Task 4: Layout Design

- Import schematic into PCB designer.

- Design 4 layer board keeping a large ground plane and minimising loop areas in switch nodes. Have separate ground planes for high resolution analogue signals vs power plane

- Order and assemble multiple boards.

## WP3: Control Electronics Design

Deliverable: Power Controller board able to interface directly with the power electronics board. Containing micro-controller, hardware signal conditioning, DCDC converters, signal isolation.

### Task 1: Control Scheme Comparison

Evaluate different control schemes: Open Loop, Closed Loop in hardware, software and hybrid approach.

### Task 2: Hardware Control Simulation

- Simulate the chosen control scheme using a simplified power stage

- Simulate the hardware sensors and controllers

### Task 3: Control Electronics Schematic

- Design a 1- or 2-page schematic with all components divided into functional block areas.

- Integrate isolation, DCDC conversion and signal conditioning.

- Use standard and reliable connectors to the power electronics board. Integrate extra connectors to integrate a DAQ board or other communication protocols

### Task 4: Control Electronics Layout

- Import schematic into PCB designer

- Design 2-layer board creating a large and continuous ground plane where possible.

- Add mounting holes and order PCBs to be assembled in Galway.

## WP4: Electrical Verification

### Deliverable: Verify the functionality of both the power electronics board and the power controller board.

### Open Loop Power Electronic Testing

- Verify bridge functionality behaves as per simulations

- The Power Electronics board can be tested open loop to verify functionality and characterise the device

- Determine maximum specifications, voltage, PWM % current etc.

### Power Controller Testing

- Verify the functionality of the hardware/software controller

- Determine isolation efficacy, response speed for current controller.

### Closed Loop Motor Control

- Connect the power electronics board to the power controller

- Run an Arduino script connecting the throttle and running an unloaded motor.

- Use a very low maximum current and use an oscilloscope to see the current limiting.

### Verification on Mini Dynamometer

- In combination with Seán Cotter’s mini dynamometer project verify functionality with different current limits on different loads

- Identify stall torques and currents and use the current limiting to meet the limits.

## WP5: Implementation on the Geec

Deliverable: Power Electronics system integrated into the Geec capable of racing at SEM

### Integrate Power Electronics into the Geec

- Create all necessary connections for the new power electronics board

- Add connections to the steering wheel and DAQ.

### Run new Power Electronic on the Dynamometer

- Complete a safe test of the new power electronics on the Dynamometer and compare the results with existing dynamometer data

- Run a variety of torques and current limits

### Complete a Track Test

- Complete a track test in Dangan or another location and run a full race as per SEM rules.

- Complete a simulated

# Work Schedule

# Risk Register

# Communication Strategy